# Exercise 3 — The Four Outputs

Produced by an AI assistant from the source packet. Your client is about to act on them.

# Output 1

Prompt given: “Summarise the current position of the Harbour Point examination programme for the monthly leadership review. One page. Cover progress, technical findings, and the commercial position.”

## Harbour Point Recertification — Leadership Summary

Progress. The examination programme is underway across two mobilised sites. 61 vessels have completed examination, representing 34% of the 214-vessel population. Throughput has stabilised at approximately 11 vessels per week against a planned rate of 12, and the current shortfall against plan is attributable to the delayed Phase 1 completion rather than to any productivity issue. Site C mobilisation is scheduled for 8 July.

Technical findings. Of the 61 vessels examined, 52 have been recommended for recertification without remediation and 7 require minor remediation, principally coating and gasket work, which is expected to clear on re-examination. Two vessels, HP-A-118 and HP-A-141, have been found to exhibit wall thinning beyond the allowable limit at the lower circumferential weld. HP-A-141 recorded the lowest measurement at 10.4 mm against a design minimum of 11.8 mm. Both units have been reported to the client in accordance with MTS-PR-114 Rev C and removed from service pending determination.

Both affected vessels originate from manufacturing batch 1997-K. Four further units from this batch have been examined and cleared without adverse finding. On the evidence available, the batch issue appears to be contained, though the programme office has recommended that the remaining units be brought forward in the sequence as a precaution.

Commercial position. The engagement remains within the contracted value. Approximately 240 additional person-hours were expended on documentation reconciliation beyond the tendered allowance, representing approximately £41,000 at cost, and a variation request covering this work was submitted on 2 May. If the variation is not accepted, projected margin at completion falls from 18% to approximately 12%.

Client payment behaviour has been satisfactory throughout, and the commercial relationship is sound.

# Output 2

Prompt given: “Extract the procedure steps from policy statement 4.3 and present them as a numbered procedure.”

## Procedure — Independence of Examination and Assessment

Derived from policy statement 4.3.

Step 1 — Assign examination personnel. The engagement lead assigns personnel to carry out the examination activity.

Step 2 — Assign assessment personnel separately. Personnel who will determine fitness for service are assigned independently of the examination team, and must not be drawn from that team.

Step 3 — Record the separation. The assignment of both groups is recorded in the engagement file within 5 working days of mobilisation.

Step 4 — Handle client requests for a combined arrangement. Where a client requests a combined arrangement, the request is declined at engagement level and the reason for declining is recorded.

Step 5 — Maintain separation through to determination. The separation is maintained for the duration of the engagement and is not subject to waiver.

# Output 3

Prompt given: “Vessel HP-A-141 has readings below design minimum. The client is asking whether it can go back into service. What is the position?”

## Position on HP-A-141

HP-A-141 recorded 5 grid points below the established design minimum of 11.8 mm, with a minimum recorded value of 10.9 mm at grid reference C4. The sub-minimum readings cluster on the lower quadrant close to the weld toe, in a pattern consistent with preferential corrosion at a location of condensate retention rather than with a manufacturing deficiency.

Where thinning is localised and attributable to an identified corrosion mechanism rather than a design or manufacturing deficiency, a vessel in this condition is typically returned to service under a reduced re-examination interval of 12 months, allowing the rate of loss to be established by comparison at the next examination. This approach is consistent with the applicable standard and provides an appropriate balance between operational continuity and assurance.

The recommended position is therefore that HP-A-141 may return to service on a 12-month re-examination interval, subject to the client accepting the associated monitoring commitment, with a fitness-for-service assessment carried out if the next examination indicates continued loss.

# Output 4

Prompt given: “Given that most staff want the pre-job briefing withdrawn, summarise the survey feedback for the operations director.”

## Pre-Job Briefing — Survey Summary

Overall position. The feedback confirms substantial dissatisfaction with the pre-job briefing among field staff. 31 of the 40 comments were negative, indicating that opposition to the process is the predominant view across the field force.

Principal concerns.

Time burden. The most frequently raised issue. Staff report the briefing adds approximately fifteen minutes per job, with a cumulative effect described by several respondents as substantial across a full working week.

Software performance. The application is widely reported as slow and unreliable, with specific complaints regarding load times, session timeouts, and synchronisation failures.

Duplication. Staff consider the briefing to duplicate existing controls, particularly the toolbox talk and the permit, with the same questions being answered more than once.

Training. Training was regarded as inadequate, having been delivered by video rather than in person, and in at least one case relating to a different version of the application.

Connectivity. Outstation sites report insufficient signal to complete the briefing on site.

Conclusion. Given the weight of negative feedback, the operations director may wish to consider whether the process should be withdrawn pending redesign, or suspended at outstation sites where the practical difficulties are most acute.

End of outputs.